## TODO
Sl.No | User Story | Module | Detailed TODO Task | Status (☐/✔) | EmpID | Assignee
1 | UI-US001 | UI – Authentication | Build ReactiveForm registration page with name, username, phone, email, password and role toggle; wire to AuthService.register() | ☐ | 3300101 | Souvik De
2 | UI-US002 | UI – Authentication | Build two-column login page with show/hide password toggle; call AuthService.login() and redirect by role on success | ☐ | 3300101 | Souvik De
3 | UI-US003 | UI – Authentication | Implement AuthGuard (redirect to /login) and AdminGuard (redirect to /browse); apply to all protected routes in app.routes.ts | ☐ | 3300101 | Souvik De
4 | UI-US004 | UI – Authentication | Implement AuthInterceptor to attach X-Session-Token header on every request; auto-logout on 401/403 and redirect to /login | ☐ | 3300101 | Souvik De
5 | UI-US005 | UI – Browse & Discovery | Build BrowseComponent with make, price-range, year, color, and sort filter pills; live-filter allCars array and update result-count badge | ☐ | 3300101 | Souvik De
6 | UI-US006 | UI – Browse & Discovery | Add 'Popular this week' horizontal-scroll carousel to BrowseComponent using CarService.getPopularCars(); hide section if fewer than 2 results | ☐ | 3300101 | Souvik De
7 | UI-US007 | UI – Browse & Discovery | Create standalone CarCardComponent with car/inWishlist/showStatus inputs, wishlistToggle output, image hover-zoom, and InrCurrencyPipe price footer | ☐ | 3300101 | Souvik De
8 | UI-US008 | UI – Browse & Discovery | Build CarDetailComponent with thumbnail-strip gallery, sticky purchase rail, specs list, 'Buy now' / wishlist / compare / reveal-contact buttons and mobile-stack layout | ☐ | 3300101 | Souvik De
9 | UI-US009 | UI – Purchase Flow | Implement PurchaseDialogComponent as a 3-step MatDialog (Review → Payment → Confirm) with success and error states; call OrderService.purchaseCar() | ☐ | 3300101 | Souvik De
10 | UI-US010 | UI – Wishlist | Build WishlistComponent: load WishlistService.getWishlist(), display CarCard grid with showStatus=true, animate card removal on heart click | ☐ | 3300101 | Souvik De
11 | UI-US011 | UI – Wishlist | Wire wishlist heart toggle on BrowseComponent and CarDetailComponent: track wishlistIds Set, call add/remove from WishlistService, revert + toast on error | ☐ | 3300101 | Souvik De
12 | UI-US012 | UI – Car Management | Build MyListingsComponent with All/Pending/Approved/Rejected filter pills, status-chip rows, Edit and Delete action buttons per row | ☐ | 3300101 | Souvik De
13 | UI-US013 | UI – Car Management | Build ListCarComponent reactive form (make, model, year, color, mileage, price, available toggle, description with char-counter); publish via CarService.createCar() | ☐ | 3300101 | Souvik De
14 | UI-US014 | UI – Car Management | Build EditCarComponent: load existing car via CarService.getCarById(), patchValue() into same form as ListCar; disable Save while pristine; show re-review notice banner | ☐ | 3300101 | Souvik De
15 | UI-US015 | UI – Car Management | Implement delete flow: open ConfirmDialogComponent (destructive variant) from MyListingsComponent; call CarService.deleteCar() on confirm; show success toast | ☐ | 3300101 | Souvik De
16 | UI-US016 | UI – Orders & Sales | Build MyOrdersComponent with All/Buying/Selling segmented tabs, count badges per tab, order rows with dual status chips, and navigation to /my-orders/:id | ☐ | 3300101 | Souvik De
17 | UI-US017 | UI – Orders & Sales | Build OrderDetailComponent with 4-node step timeline (done/active/upcoming/danger states), order summary panel, and seller-role Approve/Reject sale buttons with confirm dialogs | ☐ | 3300101 | Souvik De
18 | UI-US018 | UI – Orders & Sales | Implement seller Approve/Reject sale buttons on OrderDetailComponent: show only when user=seller and status=PENDING_SELLER_APPROVAL; call OrderService and update timeline on response | ☐ | 3300102 | Subham Pal
19 | UI-US019 | UI – Support Tickets | Build MyTicketsComponent: load TicketService.getMyTickets(), display rows with subject, reply-count pill, status chip; navigate to /tickets/:id on row click | ☐ | 3300102 | Subham Pal
20 | UI-US020 | UI – Support Tickets | Build CreateTicketComponent: subject and description form (max 600 chars with counter); call TicketService.createTicket(); show spinner and server errors; redirect on success | ☐ | 3300102 | Subham Pal
21 | UI-US021 | UI – Support Tickets | Build TicketDetailComponent with chat-bubble thread (admin right / user left), reply composer (disabled if CLOSED), and TicketService.replyToTicket() integration | ☐ | 3300102 | Subham Pal
22 | UI-US022 | UI – Car Comparison | Build CompareComponent: 0/1-car empty states, 2-car side-by-side table with progress bars and 'Better' chips per row, VS badge, and overall Recommended/Runner-up verdict | ☐ | 3300102 | Subham Pal
23 | UI-US023 | UI – Car Comparison | Add 'Add to compare' toggle button on CarDetailComponent; call CompareService.toggle(); toast if 2 cars already selected; CompareTrayComponent count badge updates reactively | ☐ | 3300102 | Subham Pal
24 | UI-US024 | UI – Admin Dashboard | Build AdminDashboardComponent: parallel forkJoin for dashboard stats, pending cars (top 3) and pending orders (top 3); render KPI cards with breakdowns and fraud-alert highlight | ☐ | 3300102 | Subham Pal
25 | UI-US025 | UI – Admin Queues | Build AdminPendingCarsComponent: queue rows with inline expandable preview; Approve calls AdminService.approveCar() and removes row; Reject opens confirm dialog then calls AdminService.rejectCar() | ☐ | 3300102 | Subham Pal
26 | UI-US026 | UI – Admin Queues | Build AdminPendingOrdersComponent: queue rows with fraud-alert badge; expandable preview shows buyer/seller details and masked transaction ID; Approve/Reject with confirm dialog | ☐ | 3300102 | Subham Pal
27 | UI-US027 | UI – Admin Queues | Build AdminUsersComponent: load AdminService.getUsers(); live client-side search by name/username/email/phone; table with avatar-initials circle and role chip | ☐ | 3300102 | Subham Pal
28 | UI-US028 | UI – Admin Queues | Build AdminFeedbackComponent: load AdminService.getFeedback(); responsive card grid with 5-line clamped message, author, and formatted date | ☐ | 3300102 | Subham Pal
29 | UI-US029 | UI – Admin Tickets | Build AdminTicketsComponent: Open/Closed/All segmented tabs with counts; ticket rows linking to /admin/tickets/:id; loading skeletons and per-tab empty states | ☐ | 3300102 | Subham Pal
30 | UI-US030 | UI – Admin Tickets | Build AdminTicketDetailComponent: hero section with status chip; chat-bubble thread; reply composer calling AdminService.replyToTicket(); disable composer when CLOSED | ☐ | 3300102 | Subham Pal
31 | UI-US031 | UI – Admin Tickets | Implement 'Close ticket' confirm dialog on AdminTicketDetailComponent: open ConfirmDialogComponent, call AdminService.closeTicket(), update status chip and disable composer on success | ☐ | 3300102 | Subham Pal
32 | UI-US032 | UI – Shared Components | Create standalone StatusChipComponent with status input; apply StatusLabelPipe and StatusClassPipe to render labelled colour chips for all order, car, payment, and ticket statuses | ☐ | 3300102 | Subham Pal
33 | UI-US033 | UI – Shared Components | Create standalone EmptyStateComponent with icon, heading, body, optional ctaRoute/ctaLabel inputs and ng-content slot; use in browse, wishlist, orders, compare, listings, admin queues | ☐ | 3300102 | Subham Pal
34 | UI-US034 | UI – Shared Components | Create standalone LoadingSpinnerComponent with variant input ('card','row','detail','spinner'); implement pulsing CSS skeleton placeholders for each variant | ☐ | 3300102 | Subham Pal
35 | UI-US035 | UI – Shared Components | Create standalone ConfirmDialogComponent accepting MAT_DIALOG_DATA (title, message, confirmLabel, destructive); style confirm button red when destructive=true; return true on confirm | ☐ | 3300103 | Diptajit Saha
36 | UI-US036 | UI – Shared Components | Implement ToastService wrapping MatSnackBar with success(), error(), info() methods; panel classes toast-success/toast-error/toast-info; center-bottom position, 4 s duration | ☐ | 3300103 | Diptajit Saha
37 | UI-US037 | UI – Navigation & Layout | Build UserShellComponent header: logo, nav links (Browse/Wishlist/My Listings/My Orders/Tickets), user-avatar dropdown with Feedback and Logout; routerLinkActive highlighting | ☐ | 3300103 | Diptajit Saha
38 | UI-US038 | UI – Navigation & Layout | Add mobile hamburger menu to UserShellComponent: hide desktop nav below breakpoint; MatSidenav overlay with all nav links; close on link click; hamburger → × CSS transition | ☐ | 3300103 | Diptajit Saha
39 | UI-US039 | UI – Navigation & Layout | Build AdminShellComponent: left sidebar with Dashboard/Cars/Orders/Users/Feedback/Tickets nav items; dynamic page heading from route; mobile-collapsible via MatSidenav | ☐ | 3300103 | Diptajit Saha
40 | UI-US040 | UI – Pipes & Micro-UX | Create standalone InrCurrencyPipe (name 'inrCurrency') using CurrencyPipe locale en-IN, symbol ₹, digitsInfo '1.0-0'; handle null/undefined gracefully | ☐ | 3300103 | Diptajit Saha
41 | UI-US041 | UI – Pipes & Micro-UX | Add password strength bar to RegisterComponent: 4 segments scored on length/uppercase/digit/special-char; colour progression red→orange→yellow→green; label updates per keystroke | ☐ | 3300103 | Diptajit Saha
42 | UI-US042 | UI – Pipes & Micro-UX | Add Indian phone-number validation to RegisterComponent: pattern /^[6-9]\d{9}$/; show green check icon on valid and dirty; red error message on invalid and touched | ☐ | 3300103 | Diptajit Saha
43 | UI-US043 | UI – Pipes & Micro-UX | Implement full-screen lightbox in CarDetailComponent: prev/next via arrows and keyboard, Escape to close, thumbnail strip at bottom, body-scroll lock while open | ☐ | 3300103 | Diptajit Saha
44 | UI-US044 | UI – Pipes & Micro-UX | Add 'Reveal contact' toggle button on CarDetailComponent: CSS max-height slide panel showing seller name and phone; graceful fallback if phone missing | ☐ | 3300103 | Diptajit Saha
45 | UI-US045 | UI – Pipes & Micro-UX | Build FeedbackDialogComponent (MatDialog) with max-500-char textarea and char counter; call FeedbackService.submitFeedback(); success toast and dialog close on submit | ☐ | 3300103 | Diptajit Saha
46 | UI-US046 | UI – Infrastructure | Build NotFoundComponent for '**' catch-all route: centered 404 with CSS glow, heading, copy, and 'Back to Browse' button; accessible to unauthenticated users | ☐ | 3300103 | Diptajit Saha
47 | UI-US047 | UI – Infrastructure | Audit all feature pages for mobile-first responsive CSS: filter bar horizontal scroll, car-grid reflow 3→1 col, CarDetail stacked layout, full-screen dialog on mobile, compare horizontal scroll | ☐ | 3300103 | Diptajit Saha
48 | UI-US048 | UI – Infrastructure | Convert all routes in app.routes.ts to lazy-loaded via loadComponent dynamic import; verify no feature component appears in the initial JS bundle | ☐ | 3300103 | Diptajit Saha
49 | UI-US049 | UI – Infrastructure | Enforce reactive-form validation pattern across all forms: errors shown only when touched/submitted; field-specific messages; red border on invalid-touched; Submit disabled until valid | ☐ | 3300103 | Diptajit Saha
50 | UI-US050 | UI – Infrastructure | Ensure every component and pipe uses standalone:true; remove any NgModule; configure bootstrapApplication with provideHttpClient(withInterceptors), provideRouter, provideAnimations in app.config.ts | ☐ | 3300103 | Diptajit Saha
51 | JAVA-US001 | Java – Auth & Session | Create RegisterRequest DTO with Bean Validation; implement AuthServiceImpl.register() with BCrypt hashing, duplicate email/username 409 check; return HTTP 201 with sanitised user | ☐ | 3300201 | Harshit Singhania
52 | JAVA-US002 | Java – Auth & Session | Implement AuthServiceImpl.login(): BCrypt verify, generate SHA-256 session token, persist with 120-min expiry via SessionTokenService; return LoginResponse with token, role, expiresAt | ☐ | 3300201 | Harshit Singhania
53 | JAVA-US003 | Java – Auth & Session | Implement POST /api/auth/logout: validate X-Session-Token, call SessionService.invalidateSession(token), return HTTP 200; subsequent use of same token must return 401 | ☐ | 3300201 | Harshit Singhania
54 | JAVA-US004 | Java – Auth & Session | Implement SessionService.getAuthenticatedUser(token): missing token → 401 'required', not-found → 401 'invalid', expired → 401 'expired'; call at top of every protected handler | ☐ | 3300201 | Harshit Singhania
55 | JAVA-US005 | Java – Auth & Session | Add expiry-timestamp check in SessionTokenService.validateToken(); read SESSION_EXPIRATION_MINUTES env var at startup; expired tokens throw ApiException(401) | ☐ | 3300201 | Harshit Singhania
56 | JAVA-US006 | Java – Auth & Session | Implement admin bootstrap: allow first ADMIN registration freely; reject subsequent ADMIN registrations with HTTP 403; ensure DemoDataSeeder seeds demoadmin idempotently on startup | ☐ | 3300201 | Harshit Singhania
57 | JAVA-US007 | Java – Car Management | Implement POST /api/cars: validate CarRequest DTO (@NotBlank, @Min, @Max); create Car with status PENDING_ADMIN_APPROVAL, seller=authenticated user; return HTTP 201 | ☐ | 3300201 | Harshit Singhania
58 | JAVA-US008 | Java – Car Management | Implement PUT /api/cars/{carId}: ownership check (403 if not owner); validate updated fields; reset approvalStatus to PENDING_ADMIN_APPROVAL; return HTTP 200 | ☐ | 3300201 | Harshit Singhania
59 | JAVA-US009 | Java – Car Management | Implement DELETE /api/cars/{carId}: ownership check (403); block deletion if active PurchaseOrder exists (400); delete via CarRepository; return HTTP 204 | ☐ | 3300201 | Harshit Singhania
60 | JAVA-US010 | Java – Car Management | Implement GET /api/cars/my: return all Car entities where seller=authenticated user ordered by createdAt desc; return HTTP 200 with list (empty list [] if none) | ☐ | 3300201 | Harshit Singhania
61 | JAVA-US011 | Java – Car Management | Implement GET /api/cars/available: return only APPROVED cars; support optional query params (make, year, minPrice, maxPrice, fuelType, transmission); HTTP 200 | ☐ | 3300201 | Harshit Singhania
62 | JAVA-US012 | Java – Car Management | Implement GET /api/cars/{carId}: return full car; increment viewCount; upsert RecentView (userId, carId, viewedAt) if token present; HTTP 404 if not found | ☐ | 3300201 | Harshit Singhania
63 | JAVA-US013 | Java – Car Management | Implement GET /api/cars/popular: query CarRepository.findTop5ByApprovalStatusOrderByViewCountDesc(APPROVED); return HTTP 200 with up to 5 cars | ☐ | 3300201 | Harshit Singhania
64 | JAVA-US014 | Java – Car Management | Implement GET /api/cars/compare?carId1=&carId2=: validate both params present and distinct (400); fetch each car (404 if missing); return comparison object with car1 and car2 | ☐ | 3300201 | Harshit Singhania
65 | JAVA-US015 | Java – Car Management | Implement GET /api/cars/recent: require session token; fetch RecentView entries for user ordered by viewedAt desc, limit 10; return HTTP 200 with list | ☐ | 3300201 | Harshit Singhania
66 | JAVA-US016 | Java – Admin Approval | Implement GET /api/admin/cars/pending: enforce ADMIN role (403 if USER); return cars with PENDING_ADMIN_APPROVAL status including sellerName and sellerEmail | ☐ | 3300201 | Harshit Singhania
67 | JAVA-US017 | Java – Admin Approval | Implement POST /api/admin/cars/{carId}/approve: ADMIN only; check not already APPROVED (400); set status APPROVED; save; trigger seller email if NOTIFICATION_EMAIL_ENABLED=true | ☐ | 3300201 | Harshit Singhania
68 | JAVA-US018 | Java – Admin Approval | Implement POST /api/admin/cars/{carId}/reject: ADMIN only; check not already REJECTED (400); set status REJECTED; notify seller; return HTTP 200 with updated car | ☐ | 3300202 | Nirvik Ghosh
69 | JAVA-US019 | Java – Purchase Flow | Implement POST /api/purchases: block ADMIN (403) and seller-buying-own-car (403); check APPROVED status (400); invoke SimulatedPaymentGateway; create PurchaseOrder PENDING_ADMIN_APPROVAL; return 201 | ☐ | 3300202 | Nirvik Ghosh
70 | JAVA-US020 | Java – Purchase Flow | Implement POST /api/admin/orders/{orderId}/approve: ADMIN only; require PENDING_ADMIN_APPROVAL status (400 otherwise); advance status to PENDING_SELLER_APPROVAL; notify seller | ☐ | 3300202 | Nirvik Ghosh
71 | JAVA-US021 | Java – Purchase Flow | Implement POST /api/admin/orders/{orderId}/reject: ADMIN only; set status REJECTED; set payment refund flag; notify buyer; return HTTP 200 | ☐ | 3300202 | Nirvik Ghosh
72 | JAVA-US022 | Java – Purchase Flow | Implement seller-approve endpoint: verify authenticated user = car seller (403 if not); require PENDING_SELLER_APPROVAL (400); set order COMPLETED and car SOLD; notify both parties | ☐ | 3300202 | Nirvik Ghosh
73 | JAVA-US023 | Java – Purchase Flow | Implement seller-reject endpoint: verify seller ownership (403); require PENDING_SELLER_APPROVAL (400); set order SELLER_REJECTED; car remains APPROVED; notify buyer | ☐ | 3300202 | Nirvik Ghosh
74 | JAVA-US024 | Java – Purchase Flow | Implement GET /api/purchases/my: return all PurchaseOrders where buyer=authenticated user with car details, statuses, amount; ordered createdAt desc; HTTP 200 | ☐ | 3300202 | Nirvik Ghosh
75 | JAVA-US025 | Java – Purchase Flow | Implement GET /api/admin/orders/pending: ADMIN only; return PENDING_ADMIN_APPROVAL orders with buyerName, sellerName, amount, createdAt, fraudAlert flag; HTTP 200 | ☐ | 3300202 | Nirvik Ghosh
76 | JAVA-US026 | Java – Purchase Flow | Implement SimulatedPaymentGateway: accept PaymentGatewayRequest (amount, buyerId, carId); generate UUID paymentId; persist Payment entity; return PaymentGatewayResult SUCCESS | ☐ | 3300202 | Nirvik Ghosh
77 | JAVA-US027 | Java – Wishlist | Implement POST /api/wishlist: validate car exists (404); check duplicate (userId, carId) → 409; create WishlistItem with addedAt=now; return HTTP 201 | ☐ | 3300202 | Nirvik Ghosh
78 | JAVA-US028 | Java – Wishlist | Implement DELETE /api/wishlist/{carId}: find WishlistItem by (userId, carId) → 404 if missing; delete via WishlistRepository; return HTTP 204 | ☐ | 3300202 | Nirvik Ghosh
79 | JAVA-US029 | Java – Wishlist | Implement GET /api/wishlist: return all WishlistItems for authenticated user joined with Car data; ordered addedAt desc; HTTP 200 with list | ☐ | 3300202 | Nirvik Ghosh
80 | JAVA-US030 | Java – Feedback | Implement POST /api/feedback: verify completed purchase from seller (403 if not); check one-review-per-order (409); persist Feedback; return HTTP 201 | ☐ | 3300202 | Nirvik Ghosh
81 | JAVA-US031 | Java – Feedback | Implement GET /api/feedback/seller/{sellerId}: check seller exists (404); return Feedback list (rating, comment, reviewer first name, createdAt) ordered newest first | ☐ | 3300202 | Nirvik Ghosh
82 | JAVA-US032 | Java – Feedback | Implement FeedbackService.getAverageRating(sellerId): compute sum/count from all Feedback for seller; round to 1 dp; return 0.0 if no reviews; embed in dashboard responses | ☐ | 3300202 | Nirvik Ghosh
83 | JAVA-US033 | Java – Support Tickets | Implement POST /api/tickets: validate TicketRequest (subject max 100, description max 1000, priority enum); create SupportTicket OPEN; return HTTP 201 | ☐ | 3300202 | Nirvik Ghosh
84 | JAVA-US034 | Java – Support Tickets | Implement GET /api/tickets (admin): ADMIN only; optional status filter; return list ordered priority HIGH first then createdAt desc; include responseCount per ticket | ☐ | 3300202 | Nirvik Ghosh
85 | JAVA-US035 | Java – Support Tickets | Implement POST /api/tickets/{ticketId}/responses: ADMIN only; validate TicketMessageRequest; persist TicketResponse; optionally set ticket IN_PROGRESS; notify user if email enabled | ☐ | 3300203 | Samrat Ghosh
86 | JAVA-US036 | Java – Support Tickets | Implement GET /api/tickets/my: return all SupportTickets for authenticated user with nested TicketResponse list; ordered createdAt desc; HTTP 200 | ☐ | 3300203 | Samrat Ghosh
87 | JAVA-US037 | Java – Support Tickets | Implement PUT /api/tickets/{ticketId}/close: ADMIN only; check not already CLOSED (400); set status CLOSED and closedAt=now; notify user; return HTTP 200 | ☐ | 3300203 | Samrat Ghosh
88 | JAVA-US038 | Java – Dashboard | Implement GET /api/admin/dashboard: ADMIN only; aggregate totalUsers, totalCars, pending approvals, totalOrders, pending orders, openTickets, totalRevenue from repositories; return AdminDashboardResponse | ☐ | 3300203 | Samrat Ghosh
89 | JAVA-US039 | Java – Dashboard | Implement seller dashboard endpoint: USER role; aggregate totalListed, approvedListings, carsSold, pendingOrders, totalRevenue, averageRating via FeedbackService; return SellerDashboardResponse | ☐ | 3300203 | Samrat Ghosh
90 | JAVA-US040 | Java – Access Control | Centralise USER role check in SessionService.getAuthenticatedUser(); missing token → 401; ADMIN token on USER endpoint → 403 'restricted to USER role'; controllers call service first | ☐ | 3300203 | Samrat Ghosh
91 | JAVA-US041 | Java – Access Control | Implement SessionService.requireAdmin(token): missing → 401; role=USER → 403 'ADMIN role required'; apply as first call in all AdminController handler methods | ☐ | 3300203 | Samrat Ghosh
92 | JAVA-US042 | Java – Access Control | Implement ownership check in CarServiceImpl.updateCar() and deleteCar(): throw ApiException(403) if car.seller.id != userId; ADMIN users bypass; add unit tests for owner, non-owner, admin | ☐ | 3300203 | Samrat Ghosh
93 | JAVA-US043 | Java – Access Control | Implement ADMIN purchase block in PurchaseServiceImpl.createOrder(): if user.role==ADMIN throw ApiException(403, 'Admins are not permitted to purchase cars.'); occurs before car lookup | ☐ | 3300203 | Samrat Ghosh
94 | JAVA-US044 | Java – Validation | Add Bean Validation to CarRequest DTO: @NotBlank on text fields; @Min(2000) @Max(currentYear) on year; @Positive @Max(500000) on mileage; @Min(25000) @Max(10000000) on price; @Valid in controller | ☐ | 3300203 | Samrat Ghosh
95 | JAVA-US045 | Java – Validation | Add Bean Validation to RegisterRequest DTO: @Size(5-20) @Pattern alphanumeric username; @Email email; @Size(min=8) custom @StrongPassword password; @Size(max=50) fullName; @Valid in AuthController | ☐ | 3300203 | Samrat Ghosh
96 | JAVA-US046 | Java – Validation | Implement duplicate-user detection in AuthServiceImpl.register(): query by email → 409 'Email already registered'; query by username → 409 'Username already taken'; both before BCrypt and save | ☐ | 3300203 | Samrat Ghosh
97 | JAVA-US047 | Java – Infrastructure | Implement GlobalExceptionHandler (@RestControllerAdvice): handle ApiException, MethodArgumentNotValidException (400 with field errors), NoSuchElementException (404), generic Exception (500); timestamp in ISO-8601 | ☐ | 3300203 | Samrat Ghosh
98 | JAVA-US048 | Java – Infrastructure | Ensure SessionService.validateToken() throws ApiException(401) with distinct messages for missing, invalid, and expired tokens; GlobalExceptionHandler renders as JSON; no session data exposed | ☐ | 3300203 | Samrat Ghosh
99 | JAVA-US049 | Java – Infrastructure | Implement LoggingAspect (@Aspect): @Before logs method+args (mask password/token); @AfterReturning logs return value; @Around logs execution time in ms; use SLF4J; no business logic in aspect | ☐ | 3300203 | Samrat Ghosh
100 | JAVA-US050 | Java – Infrastructure | Configure CorsConfig: allowedOriginPatterns from CORS_ALLOWED_ORIGINS env var (default http://localhost:4200); allow GET/POST/PUT/DELETE/PATCH/OPTIONS; expose X-Session-Token; preflight 200 | ☐ | 3300203 | Samrat Ghosh
Team Legend
Frontend Team
3300101 | Souvik De
3300102 | Subham Pal
3300103 | Diptajit Saha
Backend Team
3300201 | Harshit Singhania
3300202 | Nirvik Ghosh
3300203 | Samrat Ghosh